## Sheet1
| Name | Address | Contractor | Construction | Value | Status
1 | Steger Townhomes | East Scenic Valley Avenue | Steger Construction |  | 269500 | 601 - Finaled 7/19/18 603 - Completed. 609 - Completed. 611 - Completed. 613 - Completed. 615 - Completed. 617 - Completed. 619 - Completed. 621 - Completed. 623 - Completed.
2 | Apex Storage | 802 East Hillcrest Avenue | Andrew Hart | Storage Units | 169000 | Bldg 1 & 2 - Complete. Bldg 3 -Finaled 7/06/18
3 | CIO Properties, LC | 302 East Scenic Valley Avenue | Downing Construction | Orthodontic Clinic | 600583 | Finaled 6/20/18 Temp C.O. Issued Grade, sod landscaping by 9/01/18
4 | Indianola Community Schools | 1301 East 2nd Avenue | DDVI | Administration Building | 1544000 | Plumbing groundwork continues. C.M.U. exterior walls have begun.
5 | IMU | 1300 East Iowa Avenue | Downing Construction | Line Shop | 650000 | Structure is being erected
6 | IMU | 110 South B Street | DDVI | Fiber Shop Alteration | 476700 | Drywall install has begun
7 | St. Thomas Catholic Church | 210 R-63 Hwy. | Ball Team | Church Addition | 1672670 | Framing complete- R-I's begun
8 | Des Moines Metro Opera | 106 West Boston Avenue | Breiholz Construction | Addition/Alteration | 3300000 | Demo complete, footings for ew North additon have been placed.